## Decode Tasks
ID | DATE | YEAR | DECODE MONTH | DECODE CYCLE | DECODE DATE | ASSIGNED PERSON | ACTIVITY | STATUS | REMINDER SENT
1 | 2026-08-12 | 2026 | August | Second Friday | 2026-08-14 | Rashid | Send consensus document to Adult Decode panelists (SMEs) | Pending | Yes
2 | 2026-08-14 | 2026 | August | Second Friday | 2026-08-14 | Pathology Team | ADULT Decode | Pending | No
3 | 2026-08-14 | 2026 | August | Last Friday | 2026-08-28 | Drs. Andrew/Aziz | Send Adult Decode case packets to SMEs | Pending | No
4 | 2026-08-17 | 2026 | August | Second Friday | 2026-08-14 | Drs. Andrew/Aziz | Send Adult Decode results to Surveillance Team | Pending | No
5 | 2026-08-17 | 2026 | August | Second Friday | 2026-08-14 | Drs. Andrew/Aziz | Send Service Completion Form to Dr. Bassey | Pending | No
6 | 2026-08-17 | 2026 | August | Second Friday | 2026-08-14 | Drs. Andrew/Aziz | Upload Adult Decode report to REDCap | Pending | No
7 | 2026-08-21 | 2026 | September | Second Friday | 2026-09-11 | Data Team | Generate Adult Decode case packets | Pending | No
8 | 2026-08-24 | 2026 | August | Last Friday | 2026-08-28 | Drs. Andrew/Aziz | Send stakeholder memo for Dr. Ike's signature | Pending | No
9 | 2026-08-25 | 2026 | August | Last Friday | 2026-08-28 | SMEs | SMEs submit Adult Decode reports | Pending | No
10 | 2026-08-26 | 2026 | August | Last Friday | 2026-08-28 | Rashid | Send consensus document to Adult Decode panelists (SMEs) | Pending | No
11 | 2026-08-28 | 2026 | August | Last Friday | 2026-08-28 | Pathology Team | ADULT Decode | Pending | No
12 | 2026-08-28 | 2026 | September | Second Friday | 2026-09-11 | Drs. Andrew/Aziz | Send Adult Decode case packets to SMEs | Pending | No
13 | 2026-08-28 | 2026 | October | Last Friday | 2026-10-30 | Rashid | Send request for Network Pathology report | Pending | No
14 | 2026-08-31 | 2026 | August | Last Friday | 2026-08-28 | Drs. Andrew/Aziz | Send Adult Decode results to Surveillance Team | Pending | No
15 | 2026-08-31 | 2026 | August | Last Friday | 2026-08-28 | Drs. Andrew/Aziz | Send Service Completion Form to Dr. Bassey | Pending | No
16 | 2026-08-31 | 2026 | August | Last Friday | 2026-08-28 | Drs. Andrew/Aziz | Upload Adult Decode report to REDCap | Pending | No
17 | 2026-09-04 | 2026 | September | Last Friday | 2026-09-25 | Data Team | Generate Adult Decode case packets | Pending | No
18 | 2026-09-07 | 2026 | September | Second Friday | 2026-09-11 | Drs. Andrew/Aziz | Send stakeholder memo for Dr. Ike's signature | Pending | No
19 | 2026-09-08 | 2026 | September | Second Friday | 2026-09-11 | SMEs | SMEs submit Adult Decode reports | Pending | No
20 | 2026-09-09 | 2026 | September | Second Friday | 2026-09-11 | Rashid | Send consensus document to Adult Decode panelists (SMEs) | Pending | No
21 | 2026-09-11 | 2026 | September | Second Friday | 2026-09-11 | Pathology Team | ADULT Decode | Pending | No
22 | 2026-09-11 | 2026 | September | Last Friday | 2026-09-25 | Drs. Andrew/Aziz | Send Adult Decode case packets to SMEs | Pending | No
23 | 2026-09-11 | 2026 | November | Second Friday | 2026-11-13 | Rashid | Send request for Network Pathology report | Pending | No
24 | 2026-09-14 | 2026 | September | Second Friday | 2026-09-11 | Drs. Andrew/Aziz | Send Adult Decode results to Surveillance Team | Pending | No
25 | 2026-09-14 | 2026 | September | Second Friday | 2026-09-11 | Drs. Andrew/Aziz | Send Service Completion Form to Dr. Bassey | Pending | No
26 | 2026-09-14 | 2026 | September | Second Friday | 2026-09-11 | Drs. Andrew/Aziz | Upload Adult Decode report to REDCap | Pending | No
27 | 2026-09-18 | 2026 | October | Second Friday | 2026-10-09 | Data Team | Generate Adult Decode case packets | Pending | No
28 | 2026-09-21 | 2026 | September | Last Friday | 2026-09-25 | Drs. Andrew/Aziz | Send stakeholder memo for Dr. Ike's signature | Pending | No
29 | 2026-09-22 | 2026 | September | Last Friday | 2026-09-25 | SMEs | SMEs submit Adult Decode reports | Pending | No
30 | 2026-09-23 | 2026 | September | Last Friday | 2026-09-25 | Rashid | Send consensus document to Adult Decode panelists (SMEs) | Pending | No
31 | 2026-09-25 | 2026 | September | Last Friday | 2026-09-25 | Pathology Team | ADULT Decode | Pending | No
32 | 2026-09-25 | 2026 | October | Second Friday | 2026-10-09 | Drs. Andrew/Aziz | Send Adult Decode case packets to SMEs | Pending | No
33 | 2026-09-25 | 2026 | November | Last Friday | 2026-11-27 | Rashid | Send request for Network Pathology report | Pending | No
34 | 2026-09-28 | 2026 | September | Last Friday | 2026-09-25 | Drs. Andrew/Aziz | Send Adult Decode results to Surveillance Team | Pending | No
35 | 2026-09-28 | 2026 | September | Last Friday | 2026-09-25 | Drs. Andrew/Aziz | Send Service Completion Form to Dr. Bassey | Pending | No
36 | 2026-09-28 | 2026 | September | Last Friday | 2026-09-25 | Drs. Andrew/Aziz | Upload Adult Decode report to REDCap | Pending | No
37 | 2026-10-05 | 2026 | October | Second Friday | 2026-10-09 | Drs. Andrew/Aziz | Send stakeholder memo for Dr. Ike's signature | Pending | No
38 | 2026-10-06 | 2026 | October | Second Friday | 2026-10-09 | SMEs | SMEs submit Adult Decode reports | Pending | No
39 | 2026-10-07 | 2026 | October | Second Friday | 2026-10-09 | Rashid | Send consensus document to Adult Decode panelists (SMEs) | Pending | No
40 | 2026-10-09 | 2026 | October | Second Friday | 2026-10-09 | Pathology Team | ADULT Decode | Pending | No
41 | 2026-10-09 | 2026 | October | Last Friday | 2026-10-30 | Data Team | Generate Adult Decode case packets | Pending | No
42 | 2026-10-09 | 2026 | December | Second Friday | 2026-12-11 | Rashid | Send request for Network Pathology report | Pending | No
43 | 2026-10-12 | 2026 | October | Second Friday | 2026-10-09 | Drs. Andrew/Aziz | Send Adult Decode results to Surveillance Team | Pending | No
44 | 2026-10-12 | 2026 | October | Second Friday | 2026-10-09 | Drs. Andrew/Aziz | Send Service Completion Form to Dr. Bassey | Pending | No
45 | 2026-10-12 | 2026 | October | Second Friday | 2026-10-09 | Drs. Andrew/Aziz | Upload Adult Decode report to REDCap | Pending | No
46 | 2026-10-16 | 2026 | October | Last Friday | 2026-10-30 | Drs. Andrew/Aziz | Send Adult Decode case packets to SMEs | Pending | No
47 | 2026-10-23 | 2026 | November | Second Friday | 2026-11-13 | Data Team | Generate Adult Decode case packets | Pending | No
48 | 2026-10-23 | 2026 | December | Last Friday | 2026-12-25 | Rashid | Send request for Network Pathology report | Pending | No
49 | 2026-10-26 | 2026 | October | Last Friday | 2026-10-30 | Drs. Andrew/Aziz | Send stakeholder memo for Dr. Ike's signature | Pending | No
50 | 2026-10-27 | 2026 | October | Last Friday | 2026-10-30 | SMEs | SMEs submit Adult Decode reports | Pending | No
51 | 2026-10-28 | 2026 | October | Last Friday | 2026-10-30 | Rashid | Send consensus document to Adult Decode panelists (SMEs) | Pending | No
52 | 2026-10-30 | 2026 | October | Last Friday | 2026-10-30 | Pathology Team | ADULT Decode | Pending | No
53 | 2026-10-30 | 2026 | November | Second Friday | 2026-11-13 | Drs. Andrew/Aziz | Send Adult Decode case packets to SMEs | Pending | No
54 | 2026-11-02 | 2026 | October | Last Friday | 2026-10-30 | Drs. Andrew/Aziz | Send Adult Decode results to Surveillance Team | Pending | No
55 | 2026-11-02 | 2026 | October | Last Friday | 2026-10-30 | Drs. Andrew/Aziz | Send Service Completion Form to Dr. Bassey | Pending | No
56 | 2026-11-02 | 2026 | October | Last Friday | 2026-10-30 | Drs. Andrew/Aziz | Upload Adult Decode report to REDCap | Pending | No
57 | 2026-11-06 | 2026 | November | Last Friday | 2026-11-27 | Data Team | Generate Adult Decode case packets | Pending | No
58 | 2026-11-06 | 2027 | January | Second Friday | 2027-01-08 | Rashid | Send request for Network Pathology report | Pending | No
59 | 2026-11-09 | 2026 | November | Second Friday | 2026-11-13 | Drs. Andrew/Aziz | Send stakeholder memo for Dr. Ike's signature | Pending | No
60 | 2026-11-10 | 2026 | November | Second Friday | 2026-11-13 | SMEs | SMEs submit Adult Decode reports | Pending | No
61 | 2026-11-11 | 2026 | November | Second Friday | 2026-11-13 | Rashid | Send consensus document to Adult Decode panelists (SMEs) | Pending | No
62 | 2026-11-13 | 2026 | November | Second Friday | 2026-11-13 | Pathology Team | ADULT Decode | Pending | No
63 | 2026-11-13 | 2026 | November | Last Friday | 2026-11-27 | Drs. Andrew/Aziz | Send Adult Decode case packets to SMEs | Pending | No
64 | 2026-11-16 | 2026 | November | Second Friday | 2026-11-13 | Drs. Andrew/Aziz | Send Adult Decode results to Surveillance Team | Pending | No
65 | 2026-11-16 | 2026 | November | Second Friday | 2026-11-13 | Drs. Andrew/Aziz | Send Service Completion Form to Dr. Bassey | Pending | No
66 | 2026-11-16 | 2026 | November | Second Friday | 2026-11-13 | Drs. Andrew/Aziz | Upload Adult Decode report to REDCap | Pending | No
67 | 2026-11-20 | 2026 | December | Second Friday | 2026-12-11 | Data Team | Generate Adult Decode case packets | Pending | No
68 | 2026-11-23 | 2026 | November | Last Friday | 2026-11-27 | Drs. Andrew/Aziz | Send stakeholder memo for Dr. Ike's signature | Pending | No
69 | 2026-11-24 | 2026 | November | Last Friday | 2026-11-27 | SMEs | SMEs submit Adult Decode reports | Pending | No
70 | 2026-11-25 | 2026 | November | Last Friday | 2026-11-27 | Rashid | Send consensus document to Adult Decode panelists (SMEs) | Pending | No
71 | 2026-11-27 | 2026 | November | Last Friday | 2026-11-27 | Pathology Team | ADULT Decode | Pending | No
72 | 2026-11-27 | 2026 | December | Second Friday | 2026-12-11 | Drs. Andrew/Aziz | Send Adult Decode case packets to SMEs | Pending | No
73 | 2026-11-27 | 2027 | January | Last Friday | 2027-01-29 | Rashid | Send request for Network Pathology report | Pending | No
74 | 2026-11-30 | 2026 | November | Last Friday | 2026-11-27 | Drs. Andrew/Aziz | Send Adult Decode results to Surveillance Team | Pending | No
75 | 2026-11-30 | 2026 | November | Last Friday | 2026-11-27 | Drs. Andrew/Aziz | Send Service Completion Form to Dr. Bassey | Pending | No
76 | 2026-11-30 | 2026 | November | Last Friday | 2026-11-27 | Drs. Andrew/Aziz | Upload Adult Decode report to REDCap | Pending | No
77 | 2026-12-04 | 2026 | December | Last Friday | 2026-12-25 | Data Team | Generate Adult Decode case packets | Pending | No
78 | 2026-12-07 | 2026 | December | Second Friday | 2026-12-11 | Drs. Andrew/Aziz | Send stakeholder memo for Dr. Ike's signature | Pending | No
79 | 2026-12-08 | 2026 | December | Second Friday | 2026-12-11 | SMEs | SMEs submit Adult Decode reports | Pending | No
80 | 2026-12-09 | 2026 | December | Second Friday | 2026-12-11 | Rashid | Send consensus document to Adult Decode panelists (SMEs) | Pending | No
81 | 2026-12-11 | 2026 | December | Second Friday | 2026-12-11 | Pathology Team | ADULT Decode | Pending | No
82 | 2026-12-11 | 2026 | December | Last Friday | 2026-12-25 | Drs. Andrew/Aziz | Send Adult Decode case packets to SMEs | Pending | No
83 | 2026-12-11 | 2027 | February | Second Friday | 2027-02-12 | Rashid | Send request for Network Pathology report | Pending | No
84 | 2026-12-14 | 2026 | December | Second Friday | 2026-12-11 | Drs. Andrew/Aziz | Send Adult Decode results to Surveillance Team | Pending | No
85 | 2026-12-14 | 2026 | December | Second Friday | 2026-12-11 | Drs. Andrew/Aziz | Send Service Completion Form to Dr. Bassey | Pending | No
86 | 2026-12-14 | 2026 | December | Second Friday | 2026-12-11 | Drs. Andrew/Aziz | Upload Adult Decode report to REDCap | Pending | No
87 | 2026-12-18 | 2027 | January | Second Friday | 2027-01-08 | Data Team | Generate Adult Decode case packets | Pending | No
88 | 2026-12-21 | 2026 | December | Last Friday | 2026-12-25 | Drs. Andrew/Aziz | Send stakeholder memo for Dr. Ike's signature | Pending | No
89 | 2026-12-22 | 2026 | December | Last Friday | 2026-12-25 | SMEs | SMEs submit Adult Decode reports | Pending | No
90 | 2026-12-23 | 2026 | December | Last Friday | 2026-12-25 | Rashid | Send consensus document to Adult Decode panelists (SMEs) | Pending | No
91 | 2026-12-25 | 2026 | December | Last Friday | 2026-12-25 | Pathology Team | ADULT Decode | Pending | No
92 | 2026-12-25 | 2027 | January | Second Friday | 2027-01-08 | Drs. Andrew/Aziz | Send Adult Decode case packets to SMEs | Pending | No
93 | 2026-12-25 | 2027 | February | Last Friday | 2027-02-26 | Rashid | Send request for Network Pathology report | Pending | No
94 | 2026-12-28 | 2026 | December | Last Friday | 2026-12-25 | Drs. Andrew/Aziz | Send Adult Decode results to Surveillance Team | Pending | No
95 | 2026-12-28 | 2026 | December | Last Friday | 2026-12-25 | Drs. Andrew/Aziz | Send Service Completion Form to Dr. Bassey | Pending | No
96 | 2026-12-28 | 2026 | December | Last Friday | 2026-12-25 | Drs. Andrew/Aziz | Upload Adult Decode report to REDCap | Pending | No
97 | 2027-01-04 | 2027 | January | Second Friday | 2027-01-08 | Drs. Andrew/Aziz | Send stakeholder memo for Dr. Ike's signature | Pending | No
98 | 2027-01-05 | 2027 | January | Second Friday | 2027-01-08 | SMEs | SMEs submit Adult Decode reports | Pending | No
99 | 2027-01-06 | 2027 | January | Second Friday | 2027-01-08 | Rashid | Send consensus document to Adult Decode panelists (SMEs) | Pending | No
100 | 2027-01-08 | 2027 | January | Second Friday | 2027-01-08 | Pathology Team | ADULT Decode | Pending | No
101 | 2027-01-08 | 2027 | January | Last Friday | 2027-01-29 | Data Team | Generate Adult Decode case packets | Pending | No
102 | 2027-01-08 | 2027 | March | Second Friday | 2027-03-12 | Rashid | Send request for Network Pathology report | Pending | No
103 | 2027-01-11 | 2027 | January | Second Friday | 2027-01-08 | Drs. Andrew/Aziz | Send Adult Decode results to Surveillance Team | Pending | No
104 | 2027-01-11 | 2027 | January | Second Friday | 2027-01-08 | Drs. Andrew/Aziz | Send Service Completion Form to Dr. Bassey | Pending | No
105 | 2027-01-11 | 2027 | January | Second Friday | 2027-01-08 | Drs. Andrew/Aziz | Upload Adult Decode report to REDCap | Pending | No
106 | 2027-01-15 | 2027 | January | Last Friday | 2027-01-29 | Drs. Andrew/Aziz | Send Adult Decode case packets to SMEs | Pending | No
107 | 2027-01-22 | 2027 | February | Second Friday | 2027-02-12 | Data Team | Generate Adult Decode case packets | Pending | No
108 | 2027-01-22 | 2027 | March | Last Friday | 2027-03-26 | Rashid | Send request for Network Pathology report | Pending | No
109 | 2027-01-25 | 2027 | January | Last Friday | 2027-01-29 | Drs. Andrew/Aziz | Send stakeholder memo for Dr. Ike's signature | Pending | No
110 | 2027-01-26 | 2027 | January | Last Friday | 2027-01-29 | SMEs | SMEs submit Adult Decode reports | Pending | No
111 | 2027-01-27 | 2027 | January | Last Friday | 2027-01-29 | Rashid | Send consensus document to Adult Decode panelists (SMEs) | Pending | No
112 | 2027-01-29 | 2027 | January | Last Friday | 2027-01-29 | Pathology Team | ADULT Decode | Pending | No
113 | 2027-01-29 | 2027 | February | Second Friday | 2027-02-12 | Drs. Andrew/Aziz | Send Adult Decode case packets to SMEs | Pending | No
114 | 2027-02-01 | 2027 | January | Last Friday | 2027-01-29 | Drs. Andrew/Aziz | Send Adult Decode results to Surveillance Team | Pending | No
115 | 2027-02-01 | 2027 | January | Last Friday | 2027-01-29 | Drs. Andrew/Aziz | Send Service Completion Form to Dr. Bassey | Pending | No
116 | 2027-02-01 | 2027 | January | Last Friday | 2027-01-29 | Drs. Andrew/Aziz | Upload Adult Decode report to REDCap | Pending | No
117 | 2027-02-05 | 2027 | February | Last Friday | 2027-02-26 | Data Team | Generate Adult Decode case packets | Pending | No
118 | 2027-02-05 | 2027 | April | Second Friday | 2027-04-09 | Rashid | Send request for Network Pathology report | Pending | No
119 | 2027-02-08 | 2027 | February | Second Friday | 2027-02-12 | Drs. Andrew/Aziz | Send stakeholder memo for Dr. Ike's signature | Pending | No
120 | 2027-02-09 | 2027 | February | Second Friday | 2027-02-12 | SMEs | SMEs submit Adult Decode reports | Pending | No
121 | 2027-02-10 | 2027 | February | Second Friday | 2027-02-12 | Rashid | Send consensus document to Adult Decode panelists (SMEs) | Pending | No
122 | 2027-02-12 | 2027 | February | Second Friday | 2027-02-12 | Pathology Team | ADULT Decode | Pending | No
123 | 2027-02-12 | 2027 | February | Last Friday | 2027-02-26 | Drs. Andrew/Aziz | Send Adult Decode case packets to SMEs | Pending | No
124 | 2027-02-15 | 2027 | February | Second Friday | 2027-02-12 | Drs. Andrew/Aziz | Send Adult Decode results to Surveillance Team | Pending | No
125 | 2027-02-15 | 2027 | February | Second Friday | 2027-02-12 | Drs. Andrew/Aziz | Send Service Completion Form to Dr. Bassey | Pending | No
126 | 2027-02-15 | 2027 | February | Second Friday | 2027-02-12 | Drs. Andrew/Aziz | Upload Adult Decode report to REDCap | Pending | No
127 | 2027-02-19 | 2027 | March | Second Friday | 2027-03-12 | Data Team | Generate Adult Decode case packets | Pending | No
128 | 2027-02-22 | 2027 | February | Last Friday | 2027-02-26 | Drs. Andrew/Aziz | Send stakeholder memo for Dr. Ike's signature | Pending | No
129 | 2027-02-23 | 2027 | February | Last Friday | 2027-02-26 | SMEs | SMEs submit Adult Decode reports | Pending | No
130 | 2027-02-24 | 2027 | February | Last Friday | 2027-02-26 | Rashid | Send consensus document to Adult Decode panelists (SMEs) | Pending | No
131 | 2027-02-26 | 2027 | February | Last Friday | 2027-02-26 | Pathology Team | ADULT Decode | Pending | No
132 | 2027-02-26 | 2027 | March | Second Friday | 2027-03-12 | Drs. Andrew/Aziz | Send Adult Decode case packets to SMEs | Pending | No
133 | 2027-02-26 | 2027 | April | Last Friday | 2027-04-30 | Rashid | Send request for Network Pathology report | Pending | No
134 | 2027-03-01 | 2027 | February | Last Friday | 2027-02-26 | Drs. Andrew/Aziz | Send Adult Decode results to Surveillance Team | Pending | No
135 | 2027-03-01 | 2027 | February | Last Friday | 2027-02-26 | Drs. Andrew/Aziz | Send Service Completion Form to Dr. Bassey | Pending | No
136 | 2027-03-01 | 2027 | February | Last Friday | 2027-02-26 | Drs. Andrew/Aziz | Upload Adult Decode report to REDCap | Pending | No
137 | 2027-03-05 | 2027 | March | Last Friday | 2027-03-26 | Data Team | Generate Adult Decode case packets | Pending | No
138 | 2027-03-08 | 2027 | March | Second Friday | 2027-03-12 | Drs. Andrew/Aziz | Send stakeholder memo for Dr. Ike's signature | Pending | No
139 | 2027-03-09 | 2027 | March | Second Friday | 2027-03-12 | SMEs | SMEs submit Adult Decode reports | Pending | No
140 | 2027-03-10 | 2027 | March | Second Friday | 2027-03-12 | Rashid | Send consensus document to Adult Decode panelists (SMEs) | Pending | No
141 | 2027-03-12 | 2027 | March | Second Friday | 2027-03-12 | Pathology Team | ADULT Decode | Pending | No
142 | 2027-03-12 | 2027 | March | Last Friday | 2027-03-26 | Drs. Andrew/Aziz | Send Adult Decode case packets to SMEs | Pending | No
143 | 2027-03-12 | 2027 | May | Second Friday | 2027-05-14 | Rashid | Send request for Network Pathology report | Pending | No
144 | 2027-03-15 | 2027 | March | Second Friday | 2027-03-12 | Drs. Andrew/Aziz | Send Adult Decode results to Surveillance Team | Pending | No
145 | 2027-03-15 | 2027 | March | Second Friday | 2027-03-12 | Drs. Andrew/Aziz | Send Service Completion Form to Dr. Bassey | Pending | No
146 | 2027-03-15 | 2027 | March | Second Friday | 2027-03-12 | Drs. Andrew/Aziz | Upload Adult Decode report to REDCap | Pending | No
147 | 2027-03-19 | 2027 | April | Second Friday | 2027-04-09 | Data Team | Generate Adult Decode case packets | Pending | No
148 | 2027-03-22 | 2027 | March | Last Friday | 2027-03-26 | Drs. Andrew/Aziz | Send stakeholder memo for Dr. Ike's signature | Pending | No
149 | 2027-03-23 | 2027 | March | Last Friday | 2027-03-26 | SMEs | SMEs submit Adult Decode reports | Pending | No
150 | 2027-03-24 | 2027 | March | Last Friday | 2027-03-26 | Rashid | Send consensus document to Adult Decode panelists (SMEs) | Pending | No
151 | 2027-03-26 | 2027 | March | Last Friday | 2027-03-26 | Pathology Team | ADULT Decode | Pending | No
152 | 2027-03-26 | 2027 | April | Second Friday | 2027-04-09 | Drs. Andrew/Aziz | Send Adult Decode case packets to SMEs | Pending | No
153 | 2027-03-26 | 2027 | May | Last Friday | 2027-05-28 | Rashid | Send request for Network Pathology report | Pending | No
154 | 2027-03-29 | 2027 | March | Last Friday | 2027-03-26 | Drs. Andrew/Aziz | Send Adult Decode results to Surveillance Team | Pending | No
155 | 2027-03-29 | 2027 | March | Last Friday | 2027-03-26 | Drs. Andrew/Aziz | Send Service Completion Form to Dr. Bassey | Pending | No
156 | 2027-03-29 | 2027 | March | Last Friday | 2027-03-26 | Drs. Andrew/Aziz | Upload Adult Decode report to REDCap | Pending | No
157 | 2027-04-05 | 2027 | April | Second Friday | 2027-04-09 | Drs. Andrew/Aziz | Send stakeholder memo for Dr. Ike's signature | Pending | No
158 | 2027-04-06 | 2027 | April | Second Friday | 2027-04-09 | SMEs | SMEs submit Adult Decode reports | Pending | No
159 | 2027-04-07 | 2027 | April | Second Friday | 2027-04-09 | Rashid | Send consensus document to Adult Decode panelists (SMEs) | Pending | No
160 | 2027-04-09 | 2027 | April | Second Friday | 2027-04-09 | Pathology Team | ADULT Decode | Pending | No
161 | 2027-04-09 | 2027 | April | Last Friday | 2027-04-30 | Data Team | Generate Adult Decode case packets | Pending | No
162 | 2027-04-09 | 2027 | June | Second Friday | 2027-06-11 | Rashid | Send request for Network Pathology report | Pending | No
163 | 2027-04-12 | 2027 | April | Second Friday | 2027-04-09 | Drs. Andrew/Aziz | Send Adult Decode results to Surveillance Team | Pending | No
164 | 2027-04-12 | 2027 | April | Second Friday | 2027-04-09 | Drs. Andrew/Aziz | Send Service Completion Form to Dr. Bassey | Pending | No
165 | 2027-04-12 | 2027 | April | Second Friday | 2027-04-09 | Drs. Andrew/Aziz | Upload Adult Decode report to REDCap | Pending | No
166 | 2027-04-16 | 2027 | April | Last Friday | 2027-04-30 | Drs. Andrew/Aziz | Send Adult Decode case packets to SMEs | Pending | No
167 | 2027-04-23 | 2027 | May | Second Friday | 2027-05-14 | Data Team | Generate Adult Decode case packets | Pending | No
168 | 2027-04-23 | 2027 | June | Last Friday | 2027-06-25 | Rashid | Send request for Network Pathology report | Pending | No
169 | 2027-04-26 | 2027 | April | Last Friday | 2027-04-30 | Drs. Andrew/Aziz | Send stakeholder memo for Dr. Ike's signature | Pending | No
170 | 2027-04-27 | 2027 | April | Last Friday | 2027-04-30 | SMEs | SMEs submit Adult Decode reports | Pending | No
171 | 2027-04-28 | 2027 | April | Last Friday | 2027-04-30 | Rashid | Send consensus document to Adult Decode panelists (SMEs) | Pending | No
172 | 2027-04-30 | 2027 | April | Last Friday | 2027-04-30 | Pathology Team | ADULT Decode | Pending | No
173 | 2027-04-30 | 2027 | May | Second Friday | 2027-05-14 | Drs. Andrew/Aziz | Send Adult Decode case packets to SMEs | Pending | No
174 | 2027-05-03 | 2027 | April | Last Friday | 2027-04-30 | Drs. Andrew/Aziz | Send Adult Decode results to Surveillance Team | Pending | No
175 | 2027-05-03 | 2027 | April | Last Friday | 2027-04-30 | Drs. Andrew/Aziz | Send Service Completion Form to Dr. Bassey | Pending | No
176 | 2027-05-03 | 2027 | April | Last Friday | 2027-04-30 | Drs. Andrew/Aziz | Upload Adult Decode report to REDCap | Pending | No
177 | 2027-05-07 | 2027 | May | Last Friday | 2027-05-28 | Data Team | Generate Adult Decode case packets | Pending | No
178 | 2027-05-07 | 2027 | July | Second Friday | 2027-07-09 | Rashid | Send request for Network Pathology report | Pending | No
179 | 2027-05-10 | 2027 | May | Second Friday | 2027-05-14 | Drs. Andrew/Aziz | Send stakeholder memo for Dr. Ike's signature | Pending | No
180 | 2027-05-11 | 2027 | May | Second Friday | 2027-05-14 | SMEs | SMEs submit Adult Decode reports | Pending | No
181 | 2027-05-12 | 2027 | May | Second Friday | 2027-05-14 | Rashid | Send consensus document to Adult Decode panelists (SMEs) | Pending | No
182 | 2027-05-14 | 2027 | May | Second Friday | 2027-05-14 | Pathology Team | ADULT Decode | Pending | No
183 | 2027-05-14 | 2027 | May | Last Friday | 2027-05-28 | Drs. Andrew/Aziz | Send Adult Decode case packets to SMEs | Pending | No
184 | 2027-05-17 | 2027 | May | Second Friday | 2027-05-14 | Drs. Andrew/Aziz | Send Adult Decode results to Surveillance Team | Pending | No
185 | 2027-05-17 | 2027 | May | Second Friday | 2027-05-14 | Drs. Andrew/Aziz | Send Service Completion Form to Dr. Bassey | Pending | No
186 | 2027-05-17 | 2027 | May | Second Friday | 2027-05-14 | Drs. Andrew/Aziz | Upload Adult Decode report to REDCap | Pending | No
187 | 2027-05-21 | 2027 | June | Second Friday | 2027-06-11 | Data Team | Generate Adult Decode case packets | Pending | No
188 | 2027-05-24 | 2027 | May | Last Friday | 2027-05-28 | Drs. Andrew/Aziz | Send stakeholder memo for Dr. Ike's signature | Pending | No
189 | 2027-05-25 | 2027 | May | Last Friday | 2027-05-28 | SMEs | SMEs submit Adult Decode reports | Pending | No
190 | 2027-05-26 | 2027 | May | Last Friday | 2027-05-28 | Rashid | Send consensus document to Adult Decode panelists (SMEs) | Pending | No
191 | 2027-05-28 | 2027 | May | Last Friday | 2027-05-28 | Pathology Team | ADULT Decode | Pending | No
192 | 2027-05-28 | 2027 | June | Second Friday | 2027-06-11 | Drs. Andrew/Aziz | Send Adult Decode case packets to SMEs | Pending | No
193 | 2027-05-28 | 2027 | July | Last Friday | 2027-07-30 | Rashid | Send request for Network Pathology report | Pending | No
194 | 2027-05-31 | 2027 | May | Last Friday | 2027-05-28 | Drs. Andrew/Aziz | Send Adult Decode results to Surveillance Team | Pending | No
195 | 2027-05-31 | 2027 | May | Last Friday | 2027-05-28 | Drs. Andrew/Aziz | Send Service Completion Form to Dr. Bassey | Pending | No
196 | 2027-05-31 | 2027 | May | Last Friday | 2027-05-28 | Drs. Andrew/Aziz | Upload Adult Decode report to REDCap | Pending | No
197 | 2027-06-04 | 2027 | June | Last Friday | 2027-06-25 | Data Team | Generate Adult Decode case packets | Pending | No
198 | 2027-06-07 | 2027 | June | Second Friday | 2027-06-11 | Drs. Andrew/Aziz | Send stakeholder memo for Dr. Ike's signature | Pending | No
199 | 2027-06-08 | 2027 | June | Second Friday | 2027-06-11 | SMEs | SMEs submit Adult Decode reports | Pending | No
200 | 2027-06-09 | 2027 | June | Second Friday | 2027-06-11 | Rashid | Send consensus document to Adult Decode panelists (SMEs) | Pending | No
201 | 2027-06-11 | 2027 | June | Second Friday | 2027-06-11 | Pathology Team | ADULT Decode | Pending | No
202 | 2027-06-11 | 2027 | June | Last Friday | 2027-06-25 | Drs. Andrew/Aziz | Send Adult Decode case packets to SMEs | Pending | No
203 | 2027-06-11 | 2027 | August | Second Friday | 2027-08-13 | Rashid | Send request for Network Pathology report | Pending | No
204 | 2027-06-14 | 2027 | June | Second Friday | 2027-06-11 | Drs. Andrew/Aziz | Send Adult Decode results to Surveillance Team | Pending | No
205 | 2027-06-14 | 2027 | June | Second Friday | 2027-06-11 | Drs. Andrew/Aziz | Send Service Completion Form to Dr. Bassey | Pending | No
206 | 2027-06-14 | 2027 | June | Second Friday | 2027-06-11 | Drs. Andrew/Aziz | Upload Adult Decode report to REDCap | Pending | No
207 | 2027-06-18 | 2027 | July | Second Friday | 2027-07-09 | Data Team | Generate Adult Decode case packets | Pending | No
208 | 2027-06-21 | 2027 | June | Last Friday | 2027-06-25 | Drs. Andrew/Aziz | Send stakeholder memo for Dr. Ike's signature | Pending | No
209 | 2027-06-22 | 2027 | June | Last Friday | 2027-06-25 | SMEs | SMEs submit Adult Decode reports | Pending | No
210 | 2027-06-23 | 2027 | June | Last Friday | 2027-06-25 | Rashid | Send consensus document to Adult Decode panelists (SMEs) | Pending | No
211 | 2027-06-25 | 2027 | June | Last Friday | 2027-06-25 | Pathology Team | ADULT Decode | Pending | No
212 | 2027-06-25 | 2027 | July | Second Friday | 2027-07-09 | Drs. Andrew/Aziz | Send Adult Decode case packets to SMEs | Pending | No
213 | 2027-06-25 | 2027 | August | Last Friday | 2027-08-27 | Rashid | Send request for Network Pathology report | Pending | No
214 | 2027-06-28 | 2027 | June | Last Friday | 2027-06-25 | Drs. Andrew/Aziz | Send Adult Decode results to Surveillance Team | Pending | No
215 | 2027-06-28 | 2027 | June | Last Friday | 2027-06-25 | Drs. Andrew/Aziz | Send Service Completion Form to Dr. Bassey | Pending | No
216 | 2027-06-28 | 2027 | June | Last Friday | 2027-06-25 | Drs. Andrew/Aziz | Upload Adult Decode report to REDCap | Pending | No
217 | 2027-07-05 | 2027 | July | Second Friday | 2027-07-09 | Drs. Andrew/Aziz | Send stakeholder memo for Dr. Ike's signature | Pending | No
218 | 2027-07-06 | 2027 | July | Second Friday | 2027-07-09 | SMEs | SMEs submit Adult Decode reports | Pending | No
219 | 2027-07-07 | 2027 | July | Second Friday | 2027-07-09 | Rashid | Send consensus document to Adult Decode panelists (SMEs) | Pending | No
220 | 2027-07-09 | 2027 | July | Second Friday | 2027-07-09 | Pathology Team | ADULT Decode | Pending | No
221 | 2027-07-09 | 2027 | July | Last Friday | 2027-07-30 | Data Team | Generate Adult Decode case packets | Pending | No
222 | 2027-07-09 | 2027 | September | Second Friday | 2027-09-10 | Rashid | Send request for Network Pathology report | Pending | No
223 | 2027-07-12 | 2027 | July | Second Friday | 2027-07-09 | Drs. Andrew/Aziz | Send Adult Decode results to Surveillance Team | Pending | No
224 | 2027-07-12 | 2027 | July | Second Friday | 2027-07-09 | Drs. Andrew/Aziz | Send Service Completion Form to Dr. Bassey | Pending | No
225 | 2027-07-12 | 2027 | July | Second Friday | 2027-07-09 | Drs. Andrew/Aziz | Upload Adult Decode report to REDCap | Pending | No
226 | 2027-07-16 | 2027 | July | Last Friday | 2027-07-30 | Drs. Andrew/Aziz | Send Adult Decode case packets to SMEs | Pending | No
227 | 2027-07-23 | 2027 | August | Second Friday | 2027-08-13 | Data Team | Generate Adult Decode case packets | Pending | No
228 | 2027-07-23 | 2027 | September | Last Friday | 2027-09-24 | Rashid | Send request for Network Pathology report | Pending | No
229 | 2027-07-26 | 2027 | July | Last Friday | 2027-07-30 | Drs. Andrew/Aziz | Send stakeholder memo for Dr. Ike's signature | Pending | No
230 | 2027-07-27 | 2027 | July | Last Friday | 2027-07-30 | SMEs | SMEs submit Adult Decode reports | Pending | No
231 | 2027-07-28 | 2027 | July | Last Friday | 2027-07-30 | Rashid | Send consensus document to Adult Decode panelists (SMEs) | Pending | No
232 | 2027-07-30 | 2027 | July | Last Friday | 2027-07-30 | Pathology Team | ADULT Decode | Pending | No
233 | 2027-07-30 | 2027 | August | Second Friday | 2027-08-13 | Drs. Andrew/Aziz | Send Adult Decode case packets to SMEs | Pending | No
234 | 2027-08-02 | 2027 | July | Last Friday | 2027-07-30 | Drs. Andrew/Aziz | Send Adult Decode results to Surveillance Team | Pending | No
235 | 2027-08-02 | 2027 | July | Last Friday | 2027-07-30 | Drs. Andrew/Aziz | Send Service Completion Form to Dr. Bassey | Pending | No
236 | 2027-08-02 | 2027 | July | Last Friday | 2027-07-30 | Drs. Andrew/Aziz | Upload Adult Decode report to REDCap | Pending | No
237 | 2027-08-06 | 2027 | August | Last Friday | 2027-08-27 | Data Team | Generate Adult Decode case packets | Pending | No
238 | 2027-08-06 | 2027 | October | Second Friday | 2027-10-08 | Rashid | Send request for Network Pathology report | Pending | No
239 | 2027-08-09 | 2027 | August | Second Friday | 2027-08-13 | Drs. Andrew/Aziz | Send stakeholder memo for Dr. Ike's signature | Pending | No
240 | 2027-08-10 | 2027 | August | Second Friday | 2027-08-13 | SMEs | SMEs submit Adult Decode reports | Pending | No
241 | 2027-08-11 | 2027 | August | Second Friday | 2027-08-13 | Rashid | Send consensus document to Adult Decode panelists (SMEs) | Pending | No
242 | 2027-08-13 | 2027 | August | Second Friday | 2027-08-13 | Pathology Team | ADULT Decode | Pending | No
243 | 2027-08-13 | 2027 | August | Last Friday | 2027-08-27 | Drs. Andrew/Aziz | Send Adult Decode case packets to SMEs | Pending | No
244 | 2027-08-16 | 2027 | August | Second Friday | 2027-08-13 | Drs. Andrew/Aziz | Send Adult Decode results to Surveillance Team | Pending | No
245 | 2027-08-16 | 2027 | August | Second Friday | 2027-08-13 | Drs. Andrew/Aziz | Send Service Completion Form to Dr. Bassey | Pending | No
246 | 2027-08-16 | 2027 | August | Second Friday | 2027-08-13 | Drs. Andrew/Aziz | Upload Adult Decode report to REDCap | Pending | No
247 | 2027-08-20 | 2027 | September | Second Friday | 2027-09-10 | Data Team | Generate Adult Decode case packets | Pending | No
248 | 2027-08-23 | 2027 | August | Last Friday | 2027-08-27 | Drs. Andrew/Aziz | Send stakeholder memo for Dr. Ike's signature | Pending | No
249 | 2027-08-24 | 2027 | August | Last Friday | 2027-08-27 | SMEs | SMEs submit Adult Decode reports | Pending | No
250 | 2027-08-25 | 2027 | August | Last Friday | 2027-08-27 | Rashid | Send consensus document to Adult Decode panelists (SMEs) | Pending | No
251 | 2027-08-27 | 2027 | August | Last Friday | 2027-08-27 | Pathology Team | ADULT Decode | Pending | No
252 | 2027-08-27 | 2027 | September | Second Friday | 2027-09-10 | Drs. Andrew/Aziz | Send Adult Decode case packets to SMEs | Pending | No
253 | 2027-08-27 | 2027 | October | Last Friday | 2027-10-29 | Rashid | Send request for Network Pathology report | Pending | No
254 | 2027-08-30 | 2027 | August | Last Friday | 2027-08-27 | Drs. Andrew/Aziz | Send Adult Decode results to Surveillance Team | Pending | No
255 | 2027-08-30 | 2027 | August | Last Friday | 2027-08-27 | Drs. Andrew/Aziz | Send Service Completion Form to Dr. Bassey | Pending | No
256 | 2027-08-30 | 2027 | August | Last Friday | 2027-08-27 | Drs. Andrew/Aziz | Upload Adult Decode report to REDCap | Pending | No
257 | 2027-09-03 | 2027 | September | Last Friday | 2027-09-24 | Data Team | Generate Adult Decode case packets | Pending | No
258 | 2027-09-06 | 2027 | September | Second Friday | 2027-09-10 | Drs. Andrew/Aziz | Send stakeholder memo for Dr. Ike's signature | Pending | No
259 | 2027-09-07 | 2027 | September | Second Friday | 2027-09-10 | SMEs | SMEs submit Adult Decode reports | Pending | No
260 | 2027-09-08 | 2027 | September | Second Friday | 2027-09-10 | Rashid | Send consensus document to Adult Decode panelists (SMEs) | Pending | No
261 | 2027-09-10 | 2027 | September | Second Friday | 2027-09-10 | Pathology Team | ADULT Decode | Pending | No
262 | 2027-09-10 | 2027 | September | Last Friday | 2027-09-24 | Drs. Andrew/Aziz | Send Adult Decode case packets to SMEs | Pending | No
263 | 2027-09-10 | 2027 | November | Second Friday | 2027-11-12 | Rashid | Send request for Network Pathology report | Pending | No
264 | 2027-09-13 | 2027 | September | Second Friday | 2027-09-10 | Drs. Andrew/Aziz | Send Adult Decode results to Surveillance Team | Pending | No
265 | 2027-09-13 | 2027 | September | Second Friday | 2027-09-10 | Drs. Andrew/Aziz | Send Service Completion Form to Dr. Bassey | Pending | No
266 | 2027-09-13 | 2027 | September | Second Friday | 2027-09-10 | Drs. Andrew/Aziz | Upload Adult Decode report to REDCap | Pending | No
267 | 2027-09-17 | 2027 | October | Second Friday | 2027-10-08 | Data Team | Generate Adult Decode case packets | Pending | No
268 | 2027-09-20 | 2027 | September | Last Friday | 2027-09-24 | Drs. Andrew/Aziz | Send stakeholder memo for Dr. Ike's signature | Pending | No
269 | 2027-09-21 | 2027 | September | Last Friday | 2027-09-24 | SMEs | SMEs submit Adult Decode reports | Pending | No
270 | 2027-09-22 | 2027 | September | Last Friday | 2027-09-24 | Rashid | Send consensus document to Adult Decode panelists (SMEs) | Pending | No
271 | 2027-09-24 | 2027 | September | Last Friday | 2027-09-24 | Pathology Team | ADULT Decode | Pending | No
272 | 2027-09-24 | 2027 | October | Second Friday | 2027-10-08 | Drs. Andrew/Aziz | Send Adult Decode case packets to SMEs | Pending | No
273 | 2027-09-24 | 2027 | November | Last Friday | 2027-11-26 | Rashid | Send request for Network Pathology report | Pending | No
274 | 2027-09-27 | 2027 | September | Last Friday | 2027-09-24 | Drs. Andrew/Aziz | Send Adult Decode results to Surveillance Team | Pending | No
275 | 2027-09-27 | 2027 | September | Last Friday | 2027-09-24 | Drs. Andrew/Aziz | Send Service Completion Form to Dr. Bassey | Pending | No
276 | 2027-09-27 | 2027 | September | Last Friday | 2027-09-24 | Drs. Andrew/Aziz | Upload Adult Decode report to REDCap | Pending | No
277 | 2027-10-04 | 2027 | October | Second Friday | 2027-10-08 | Drs. Andrew/Aziz | Send stakeholder memo for Dr. Ike's signature | Pending | No
278 | 2027-10-05 | 2027 | October | Second Friday | 2027-10-08 | SMEs | SMEs submit Adult Decode reports | Pending | No
279 | 2027-10-06 | 2027 | October | Second Friday | 2027-10-08 | Rashid | Send consensus document to Adult Decode panelists (SMEs) | Pending | No
280 | 2027-10-08 | 2027 | October | Second Friday | 2027-10-08 | Pathology Team | ADULT Decode | Pending | No
281 | 2027-10-08 | 2027 | October | Last Friday | 2027-10-29 | Data Team | Generate Adult Decode case packets | Pending | No
282 | 2027-10-08 | 2027 | December | Second Friday | 2027-12-10 | Rashid | Send request for Network Pathology report | Pending | No
283 | 2027-10-11 | 2027 | October | Second Friday | 2027-10-08 | Drs. Andrew/Aziz | Send Adult Decode results to Surveillance Team | Pending | No
284 | 2027-10-11 | 2027 | October | Second Friday | 2027-10-08 | Drs. Andrew/Aziz | Send Service Completion Form to Dr. Bassey | Pending | No
285 | 2027-10-11 | 2027 | October | Second Friday | 2027-10-08 | Drs. Andrew/Aziz | Upload Adult Decode report to REDCap | Pending | No
286 | 2027-10-15 | 2027 | October | Last Friday | 2027-10-29 | Drs. Andrew/Aziz | Send Adult Decode case packets to SMEs | Pending | No
287 | 2027-10-22 | 2027 | November | Second Friday | 2027-11-12 | Data Team | Generate Adult Decode case packets | Pending | No
288 | 2027-10-25 | 2027 | October | Last Friday | 2027-10-29 | Drs. Andrew/Aziz | Send stakeholder memo for Dr. Ike's signature | Pending | No
289 | 2027-10-26 | 2027 | October | Last Friday | 2027-10-29 | SMEs | SMEs submit Adult Decode reports | Pending | No
290 | 2027-10-27 | 2027 | October | Last Friday | 2027-10-29 | Rashid | Send consensus document to Adult Decode panelists (SMEs) | Pending | No
291 | 2027-10-29 | 2027 | October | Last Friday | 2027-10-29 | Pathology Team | ADULT Decode | Pending | No
292 | 2027-10-29 | 2027 | November | Second Friday | 2027-11-12 | Drs. Andrew/Aziz | Send Adult Decode case packets to SMEs | Pending | No
293 | 2027-10-29 | 2027 | December | Last Friday | 2027-12-31 | Rashid | Send request for Network Pathology report | Pending | No
294 | 2027-11-01 | 2027 | October | Last Friday | 2027-10-29 | Drs. Andrew/Aziz | Send Adult Decode results to Surveillance Team | Pending | No
295 | 2027-11-01 | 2027 | October | Last Friday | 2027-10-29 | Drs. Andrew/Aziz | Send Service Completion Form to Dr. Bassey | Pending | No
296 | 2027-11-01 | 2027 | October | Last Friday | 2027-10-29 | Drs. Andrew/Aziz | Upload Adult Decode report to REDCap | Pending | No
297 | 2027-11-05 | 2027 | November | Last Friday | 2027-11-26 | Data Team | Generate Adult Decode case packets | Pending | No
298 | 2027-11-08 | 2027 | November | Second Friday | 2027-11-12 | Drs. Andrew/Aziz | Send stakeholder memo for Dr. Ike's signature | Pending | No
299 | 2027-11-09 | 2027 | November | Second Friday | 2027-11-12 | SMEs | SMEs submit Adult Decode reports | Pending | No
300 | 2027-11-10 | 2027 | November | Second Friday | 2027-11-12 | Rashid | Send consensus document to Adult Decode panelists (SMEs) | Pending | No
301 | 2027-11-12 | 2027 | November | Second Friday | 2027-11-12 | Pathology Team | ADULT Decode | Pending | No
302 | 2027-11-12 | 2027 | November | Last Friday | 2027-11-26 | Drs. Andrew/Aziz | Send Adult Decode case packets to SMEs | Pending | No
303 | 2027-11-15 | 2027 | November | Second Friday | 2027-11-12 | Drs. Andrew/Aziz | Send Adult Decode results to Surveillance Team | Pending | No
304 | 2027-11-15 | 2027 | November | Second Friday | 2027-11-12 | Drs. Andrew/Aziz | Send Service Completion Form to Dr. Bassey | Pending | No
305 | 2027-11-15 | 2027 | November | Second Friday | 2027-11-12 | Drs. Andrew/Aziz | Upload Adult Decode report to REDCap | Pending | No
306 | 2027-11-19 | 2027 | December | Second Friday | 2027-12-10 | Data Team | Generate Adult Decode case packets | Pending | No
307 | 2027-11-22 | 2027 | November | Last Friday | 2027-11-26 | Drs. Andrew/Aziz | Send stakeholder memo for Dr. Ike's signature | Pending | No
308 | 2027-11-23 | 2027 | November | Last Friday | 2027-11-26 | SMEs | SMEs submit Adult Decode reports | Pending | No
309 | 2027-11-24 | 2027 | November | Last Friday | 2027-11-26 | Rashid | Send consensus document to Adult Decode panelists (SMEs) | Pending | No
310 | 2027-11-26 | 2027 | November | Last Friday | 2027-11-26 | Pathology Team | ADULT Decode | Pending | No
311 | 2027-11-26 | 2027 | December | Second Friday | 2027-12-10 | Drs. Andrew/Aziz | Send Adult Decode case packets to SMEs | Pending | No
312 | 2027-11-29 | 2027 | November | Last Friday | 2027-11-26 | Drs. Andrew/Aziz | Send Adult Decode results to Surveillance Team | Pending | No
313 | 2027-11-29 | 2027 | November | Last Friday | 2027-11-26 | Drs. Andrew/Aziz | Send Service Completion Form to Dr. Bassey | Pending | No
314 | 2027-11-29 | 2027 | November | Last Friday | 2027-11-26 | Drs. Andrew/Aziz | Upload Adult Decode report to REDCap | Pending | No
315 | 2027-12-06 | 2027 | December | Second Friday | 2027-12-10 | Drs. Andrew/Aziz | Send stakeholder memo for Dr. Ike's signature | Pending | No
316 | 2027-12-07 | 2027 | December | Second Friday | 2027-12-10 | SMEs | SMEs submit Adult Decode reports | Pending | No
317 | 2027-12-08 | 2027 | December | Second Friday | 2027-12-10 | Rashid | Send consensus document to Adult Decode panelists (SMEs) | Pending | No
318 | 2027-12-10 | 2027 | December | Second Friday | 2027-12-10 | Pathology Team | ADULT Decode | Pending | No
319 | 2027-12-10 | 2027 | December | Last Friday | 2027-12-31 | Data Team | Generate Adult Decode case packets | Pending | No
320 | 2027-12-13 | 2027 | December | Second Friday | 2027-12-10 | Drs. Andrew/Aziz | Send Adult Decode results to Surveillance Team | Pending | No
321 | 2027-12-13 | 2027 | December | Second Friday | 2027-12-10 | Drs. Andrew/Aziz | Send Service Completion Form to Dr. Bassey | Pending | No
322 | 2027-12-13 | 2027 | December | Second Friday | 2027-12-10 | Drs. Andrew/Aziz | Upload Adult Decode report to REDCap | Pending | No
323 | 2027-12-17 | 2027 | December | Last Friday | 2027-12-31 | Drs. Andrew/Aziz | Send Adult Decode case packets to SMEs | Pending | No
324 | 2027-12-27 | 2027 | December | Last Friday | 2027-12-31 | Drs. Andrew/Aziz | Send stakeholder memo for Dr. Ike's signature | Pending | No
325 | 2027-12-28 | 2027 | December | Last Friday | 2027-12-31 | SMEs | SMEs submit Adult Decode reports | Pending | No
326 | 2027-12-29 | 2027 | December | Last Friday | 2027-12-31 | Rashid | Send consensus document to Adult Decode panelists (SMEs) | Pending | No
327 | 2027-12-31 | 2027 | December | Last Friday | 2027-12-31 | Pathology Team | ADULT Decode | Pending | No
328 | 2028-01-03 | 2027 | December | Last Friday | 2027-12-31 | Drs. Andrew/Aziz | Send Adult Decode results to Surveillance Team | Pending | No
329 | 2028-01-03 | 2027 | December | Last Friday | 2027-12-31 | Drs. Andrew/Aziz | Send Service Completion Form to Dr. Bassey | Pending | No
330 | 2028-01-03 | 2027 | December | Last Friday | 2027-12-31 | Drs. Andrew/Aziz | Upload Adult Decode report to REDCap | Pending | No